## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-101 | As a user, I want to integrate Selenium for automated UI testing so that I can validate web application functionality | Must Have | Selenium setup, WebDriver configuration | Ayush | Completed
Sprint 1 | Sprint 1 | US-102 | As a user, I want to integrate REST-Assured for API testing to validate backend services | Must Have | REST API endpoints, Postman testing | Ayush | Completed
Sprint 2 | Sprint 2 | US-103 | As a user, I want to create Spring Boot APIs to trigger and manage test execution | Must Have | Spring Boot setup, controller design | Ayush | Completed
Sprint 2 | Sprint 2 | US-104 | As a user, I want to implement parallel test execution using multithreading to improve performance | Must Have | Java multithreading, ExecutorService | Ayush | Completed
Sprint 2 | Sprint 2 | US-105 | As a user, I want to implement test scheduling to automatically run test suites at fixed intervals | Should Have | Spring Boot scheduler, cron configuration | Ayush | Completed
Sprint 3 | Sprint 3 | US-106 | As a user, I want to store test execution results in a database for analysis | Must Have | MySQL database, JDBC integration | Ayush | Completed
Sprint 3 | Sprint 3 | US-107 | As a user, I want to generate reports (HTML/CSV) for test execution results | Should Have | File handling, report generation logic | Ayush | Completed
Sprint 3 | Sprint 3 | US-108 | As a user, I want to view analytics and dashboard for test results visualization | Could Have | Chart.js, Thymeleaf UI | Ayush | Completed
Sprint 3 | Sprint 3 | US-109 | As a user, I want APIs to fetch logs, analytics, and individual test results | Must Have | Spring Boot APIs, service layer | Ayush | Completed
Sprint 3 | Sprint 3 | US-110 | As a user, I want to perform end-to-end testing and ensure system stability | Must Have | Full system integration | Ayush | Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 110 | 3 | 5 | 9 | 12 | 16 | 16 | 15 | 15 | 9 | 8 | 2 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-101 | T1 | Selenium + REST-Assured Integration | 2026-02-25 | 2026-02-28 | Ayush | Development | Completed | 16 | 3 | 3 | 4 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-102 | T2 | Spring Boot APIs + Test Execution | 2026-02-27 | 2026-03-02 | Ayush | Development | Completed | 18 | 0 | 2 | 3 | 4 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-103 | T3 | Multithreading + Scheduler | 2026-03-01 | 2026-03-05 | Ayush | Development | Completed | 20 | 0 | 0 | 2 | 3 | 4 | 4 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0
US-104 | T4 | Reporting + Dashboard | 2026-03-03 | 2026-03-07 | Ayush | Development | Completed | 22 | 0 | 0 | 0 | 2 | 3 | 4 | 4 | 4 | 3 | 2 | 0 | 0 | 0 | 0
US-105 | T5 | Database + Analytics Integration | 2026-03-05 | 2026-03-09 | Ayush | Development | Completed | 20 | 0 | 0 | 0 | 0 | 2 | 3 | 4 | 4 | 3 | 4 | 0 | 0 | 0 | 0
US-106 | T6 | End-to-End Testing, Bug Fixing & Performance Optimization | 2026-03-08 | 2026-03-10 | Ayush | Testing | Completed | 14 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 3 | 2 | 2 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Selenium setup issues | Fixed WebDriver configuration
Sprint 1 | Day 2 | REST-Assured integration confusion | Structured dependencies properly
Sprint 1 | Day 3 | UI + API execution conflict | Created separate test runners
Sprint 1 | Day 4 | API not triggering execution | Fixed Spring Boot controller
Sprint 1 | Day 5 | Execution errors in test classes | Debugged and refactored code
Sprint 1 | Day 6 | Logging not clear | Added structured logging
Sprint 1 | Day 7 | Screenshot capture issues | Implemented failure capture logic
Sprint 2 | Day 1 | Multithreading complexity | Implemented ExecutorService
Sprint 2 | Day 2 | Parallel execution instability | Fixed thread synchronization
Sprint 2 | Day 3 | Scheduler not working | Fixed @Scheduled config
Sprint 2 | Day 4 | Report generation errors | Debugged HTML/CSV logic
Sprint 2 | Day 5 | Logs not tracking correctly | Improved logging system
Sprint 2 | Day 6 | Dashboard data mismatch | Fixed backend data mapping
Sprint 2 | Day 7 | Chart visualization issues | Corrected Chart.js integration
Sprint 3 | Day 1 | DB connection issues | Fixed JDBC configuration
Sprint 3 | Day 2 | Data not storing properly | Corrected SQL queries
Sprint 3 | Day 3 | Analytics incorrect results | Improved service logic
Sprint 3 | Day 4 | API response delays | Optimized queries
Sprint 3 | Day 5 | Integration issues | Fixed module connections
Sprint 3 | Day 6 | End-to-end bugs | Performed full testing
Sprint 3 | Day 7 | Final stability issues | Fixed minor bugs & optimized
Sprint 3 | Day 8 | Report validation issues | Verified output correctness
Sprint 3 | Day 9 | Analytics mismatch | Cross-checked DB data
Sprint 3 | Day 10 | Final testing issues | Debugged workflow
Sprint 3 | Day 11 | Documentation pending | Prepared project docs
Sprint 3 | Day 12 | Demo preparation | Tested all APIs & UI
Sprint 3 | Day 13 | Minor UI bugs | Fixed dashboard issues
Sprint 3 | Day 14 | Viva preparation | Reviewed complete system

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 25-02-2026 | 2026-03-03 | Ayush | Started Selenium & REST-Assured integration | Stopped unstructured coding | Continued learning automation tools | Setup base framework and validated UI/API execution
2 | Sprint 1 | 2026-04-03 | 2026-10-03 | Ayush | Started building Spring Boot APIs | Stopped debugging without logs | Continued improving code structure | Developed APIs to trigger test execution
3 | Sprint 2 | 2026-11-03 | 17-03-2026 | Ayush | Started multithreading & scheduling | Stopped sequential execution approach | Continued backend optimization | Implemented ExecutorService and scheduling system
4 | Sprint 2 | 18-03-2026 | 24-03-2026 | Ayush | Started report generation & logging | Stopped manual result tracking | Continued improving debugging | Built HTML/CSV reports and logging system
5 | Sprint 3 | 25-03-2026 | 29-03-2026 | Ayush | Started database integration | Stopped storing temporary results | Continued API improvements | Integrated MySQL with JDBC and stored test results
6 | Sprint 3 | 30-03-2026 | 2026-02-04 | Ayush | Started analytics & dashboard | Stopped ignoring data validation | Continued frontend-backend integration | Built analytics APIs and dashboard visualization
7 | Sprint 3 | 2026-03-04 | 2026-05-04 | Ayush | Started final testing & optimization | Stopped adding new features | Continued bug fixing & improvements | Completed end-to-end testing and prepared for demo